## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | enter an IP address to scan ports | Must | No Dependency | SP Keerthi | Done
S1 | S1 | US-001 | detect open ports using Nmap | Must | User input (IP) | SP Keerthi | Done
S1 | S2 | US-001 | detect vulnerabilities based on ports | Must | Port scanning | SP Keerthi | Done
S2 | S2 | US-001 | risk scores for vulnerabilities | Must | Vulnerability detection | SP Keerthi | Done
S2 | S2 | US-001 | results stored in database | Must | Risk calculation | SP Keerthi | Done
S2 | S2 | US-001 | view results in a table | Must | Database | SP Keerthi | Done
S3 | S3 | US-001 | charts for risk analysis | Should | Display results | SP Keerthi | Done
S3 | S3 | US-001 | threat intelligence from VirusTotal | Should | User input (IP) | SP Keerthi | Done
S3 | S3 | US-001 | PDF report generation | Could | Database | SP Keerthi | Done
S3 | S3 | US-001 | alerts for high-risk vulnerabilities | Must | Risk calculation | SP Keerthi | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 46 | 2 | 5 | 5 | 3 | 2 | 4 | 5 | 2 | 3 | 5 | 5 | 4 | 1 | 0
SPRINT 1 BACKLOG
US-001 | T1 | Create Flask app setup | 2026-03-15 | 2026-03-16 | SP Keerthi | Backend | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T2 | Implement port scanner (Nmap) | 2026-03-16 | 2026-03-17 | SP Keerthi | Backend | Done | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T3 | Create vulnerability mapping | 2026-03-17 | 2026-03-18 | SP Keerthi | Backend | Done | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T4 | Implement risk engine | 2026-03-19 | 2026-03-20 | SP Keerthi | Backend | Done | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T5 | Setup SQLite database | 2026-03-20 | 2026-03-21 | SP Keerthi | Backend | Done | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T6 | Display results in HTML | 2026-03-21 | 2026-03-22 | SP Keerthi | Frontend | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T7 | Add charts using Chart.js | 2026-03-23 | 2026-03-24 | SP Keerthi | Frontend | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
US-001 | T8 | Integrate VirusTotal API | 2026-03-24 | 2026-03-25 | SP Keerthi | Backend | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
US-001 | T9 | Generate PDF report | 2026-03-25 | 2026-03-26 | SP Keerthi | Backend | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US-001 | T10 | Add alert system | 2026-03-26 | 2026-03-27 | SP Keerthi | Backend | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-03-15 | Flask setup confusion | Watched tutorials
Sprint 1 | 2026-03-16 | Nmap installation issue | Installed dependencies
Sprint 1 | 2026-03-17 | Port scanning errors | Debugged code
Sprint 2 | 2026-03-20 | DB connection issues | Fixed SQLite logic
Sprint 2 | 2026-03-21 | Data not displaying | Fixed HTML rendering
Sprint 3 | 2026-03-25 | Chart.js not working | Corrected script
Sprint 3 | 2026-03-26 | API errors | Handled exceptions
Sprint 3 | 2026-03-27 | PDF formatting issue | Adjusted layout

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 15-03-20226 | 2026-03-19 | SP Keerthi | Learn Flask deeply | Avoid delays | Coding daily | Improved backend
2 | Sprint 2 | 2026-03-20 | 2026-03-24 | SP Keerthi | Better DB design | Avoid errors | Testing code | Improved DB logic
3 | Sprint 3 | 2026-03-25 | 2026-03-27 | SP Keerthi | Add APIs | Avoid bugs | UI improvements | Added charts & reports